## Gantt Chart
Data Science Project Timeline Gantt Chart
A bar chart which shows the schedule for my project.
[5 empty] | W 1 | W 2 | W 3 | W 4 | W 5 | W 6 | W 7 | W 8 | W 9 | W 10 | W 11 | W 12 | W 13 | W 14
Task Name | Start | End | %Completion | Status | 2025-02-11 | 2025-02-18 | 2025-02-25 | 2025-03-04 | 2025-03-11 | 2025-03-18 | 2025-03-25 | 2025-04-01 | 2025-04-08 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-05-06 | 2025-05-13
[5 empty] | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue
Data Collection & Literature Review |  |  | 0% | Upcoming
Data Collection | 2025-02-11 | 2025-02-17
Git Hub Repository | 2025-02-11 | 2025-02-17
Literature Review | 2025-02-18 | 2025-02-24
Data Cleaning & Exploratory Analysis |  |  | 0% | Upcoming
Data Cleaning | 2025-02-25 | 2025-03-03
Exploratory Data Analysis | 2025-03-04 | 2025-03-10
Model Building & Evaluation |  |  | 0% | Upcoming
Models selection | 2025-03-11 | 2025-03-17
Training the selected models | 2025-03-11 | 2025-03-17
Hyper parameter tuning | 2025-03-11 | 2025-03-17
Model Comparision | 2025-03-18 | 2025-03-24
Interpretation & Evaluation | 2025-03-18 | 2025-03-24
Final Report |  |  | 0% | Upcoming
Final Report Work | 2025-03-25 | 2025-04-21
Meet with supervisor | 2025-03-25 | 2025-04-21
Finalising the report | 2025-04-22 | 2025-05-01
Viva Preparation |  |  | 0% | Upcoming
Viva Preparation | 2025-05-03 | 2025-05-13

## Instructions
The following are instructions on how to use the template.
1. Edit or add content like inserting rows and columns to the template.
2. There are no locked-up cells for easier editing of cell names.
3. Feel free to change any formula available.
Should you need assistance, please contact our Customer Support Team using the chat box found on the website.